## Breakdown
SEO Retainer Breakdown
Client: | Sample Retail Co
Service |  | Consulting Hours | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  | Technical Hours | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
|  | Content Hours | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  | Link Hours | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6

## 1. Client Detail
SEO Retainer Agreement
---
Client Name | Sample Retail Co
Industry | Fashion
Monthly Retainer | AUD 5000
Project Start Date | 2026-07-01
CMS | Shopify
Primary Contact | Jane Smith
Account Manager | John Doe
Contract Period | 12 months

## 2. Consulting
Task | Focus | Occurrence | Hours
Monthly Strategy Review | Strategy | Monthly | 4
Keyword Research & Mapping | Strategy | Quarterly | 8
Competitor Analysis | Strategy | Quarterly | 6
GA4 & GSC Reporting | Analytics | Monthly | 3
Content Gap Analysis | Strategy | Bi-Annual | 8

## 3. Technical
Task | Focus | Occurrence | Hours
Core Web Vitals Audit | Technical | Quarterly | 6
Crawl Error Remediation | Technical | Monthly | 4
Schema Markup Implementation | Technical | Quarterly | 8
Site Speed Optimisation | Technical | Monthly | 4
Internal Linking Audit | Technical | Bi-Annual | 10

## 4. Content
Content Production Plan
12-Month Schedule
Month | Month Name | URL | Title | Focus | Priority | Content Type | Word Count | SEO Hours
1 | July | /blog/summer-fashion-guide | Summer Fashion Guide 2026 | Content | High | New Page - Long Form | 2000 | 3
1 | July | /faq/how-to-style-denim | How to Style Denim - FAQ | Content | Medium | FAQ Page | 800 | 2
2 | August | /blog/spring-trends | Spring Trends 2026 | Content | High | New Page - Long Form | 1800 | 3
2 | August | /categories/womens-dresses | Women's Dresses Category | Content | High | Optimisation | 500 | 2
3 | September | /blog/workwear-essentials | Workwear Essentials Guide | Content | Medium | New Page - Long Form | 2200 | 4
3 | September | /products/classic-blazer | Classic Blazer Product Page | Content | Low | Optimisation | 400 | 1
4 | October | /blog/autumn-layering | Autumn Layering Techniques | Content | High | New Page - Long Form | 1900 | 3

## 5. Links
Task | Focus | Occurrence | Hours
Digital PR Outreach | Off-Page | Monthly | 4
Guest Post Sourcing | Off-Page | Monthly | 2
Link Reclamation | Off-Page | Quarterly | 3