## 1. Client Detail
SEO Retainer Agreement
Client Name | Helen Kaminski
Industry | Accessories
Project Start Date | 2026-01-01
Monthly Retainer (excl tech fees) | 4906
Main POC | poc@helenkaminski.com.au
Pattern Client Partner | partner@pattern.com
Pattern SEO Lead | lead@pattern.com
Strategy Slides | HK Strategy Deck 2026
Keyword Research | HK Keyword Research 2026
Reporting Document | HK Monthly Report
TOV Document | HK Brand Voice Guide.pdf
Content Ways of Working | Content goes through HK brand review

## Breakdown
SEO Retainer Breakdown
|  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
Monthly Retainer | 4906 | Consulting Hours | 8 | 8 | 8 | 8 | 8 | 15 | 8 | 8 | 8 | 8 | 8 | 8
Hours P/M | 23.28 | Technical Hours | 0 | 0 | 6 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost P/H | 200 | Content Hours | 9.9 | 7.8 | 14.3 | 15.8 | 11.5 | 8.8 | 0 | 0 | 0 | 0 | 0 | 0
|  | Link Hours | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Hours Allocated | 17.9 | 15.8 | 28.3 | 25.8 | 23.5 | 23.8 | 8 | 8 | 8 | 8 | 8 | 8
|  | Hours to Use | 23.28 | 23.28 | 23.28 | 23.28 | 23.28 | 23.28 | 23.28 | 23.28 | 23.28 | 23.28 | 23.28 | 23.28
|  | % of Retainer | 77 | 68 | 122 | 111 | 101 | 102 | 34 | 34 | 34 | 34 | 34 | 34

## 2. Consulting
Task | Description | Hours | Cadence
Monthly Strategy Meeting | Monthly strategic direction call with client | 1 | Monthly
Monthly Reporting | GA4 + GSC monthly report and dashboard update | 2 | Monthly
Competitor Analysis | Competitive landscape review | 4 | Quarterly
Keyword Research & Mapping | Full keyword universe mapping to site architecture | 8 | Bi-Annual
Content Gap Analysis | Identify content opportunities vs. competitors | 4 | Quarterly
SEO Health Check | Comprehensive site health audit and scoring | 2 | Monthly
QBR Presentation | Quarterly business review deck preparation | 3 | Quarterly
Onboarding | Initial strategy, brand review and setup | 8 | Onboarding Month

## 3. Technical
Task | Description | Hours | Cadence
CMS: | Shopify
Technical SEO Audit | Full crawl, redirect audit, coverage analysis | 6 | Monthly
Core Web Vitals Remediation | CWV fixes: LCP, CLS, FID | 2 | Monthly
Schema Markup Implementation | Product, breadcrumb, org schema markup | 4 | Monthly
Crawl Error Monitoring | Monitor and resolve crawl errors via GSC | 1 | Monthly
Site Speed Optimisation | Image compression, lazy load, CDN config | 2 | Quarterly

## 4. Content
Month | Month Name | Content Name | URL | Total Words | Content Type | Keywords | Content Brief Detail | FAQ Questions | SEO Hours | Template set-up | Production time | SEO Review Time | SEO Implementation time
Month 1 | January 2026 | Homepage | https://helenkaminski.com.au/ | 300 | New Page: Optimisation | helen kaminski hats |  |  | 2 | 0.5 | 1 | 0.5 | 0.5
Month 1 | January 2026 | Womens Hats Collection | https://helenkaminski.com.au/collections/womens-hats | 300 | Existing Copy: Optimisation | womens hats australia |  |  | 2 | 0.5 | 1 | 0.5 | 0.5
Month 1 | January 2026 | Straw Hats | https://helenkaminski.com.au/collections/straw-hats | 300 | Existing Copy: Optimisation & FAQs | straw hats |  |  | 2 | 0.5 | 1 | 0.5 | 0.5
Month 1 | January 2026 | Summer Hats | https://helenkaminski.com.au/collections/summer-hats | 300 | New Page: Optimisation & FAQs | summer hats |  |  | 2 | 0.5 | 1 | 0.5 | 0.5
Month 1 | January 2026 | Beach Hats | https://helenkaminski.com.au/collections/beach-hats | 300 | Existing Copy: Optimisation | beach hats |  |  | 2 | 0.5 | 1 | 0.5 | 0.5
Month 1 | January 2026 | Homepage US | https://helenkaminski.com/ | 150 | New Page: Optimisation | helen kaminski hats | localisation |  | 1 | 0.5 | 0.5 | 0.5 | 0
Month 1 | January 2026 | Womens Hats US | https://helenkaminski.com/collections/womens-hats | 150 | Existing Copy: Optimisation | womens hats | localisation |  | 1 | 0.5 | 0.5 | 0.5 | 0
Month 2 | February 2026 | Sun Hats | https://helenkaminski.com.au/collections/sun-hats | 300 | Existing Copy: Optimisation | sun hats australia |  |  | 2 | 0.5 | 1 | 0.5 | 0.5
Month 2 | February 2026 | Hats Blog Post | https://helenkaminski.com.au/blogs/news/hat-guide | 500 | New Page: Optimisation | how to choose a hat |  |  | 2.5 | 0.5 | 1.5 | 0.5 | 0.5
Month 2 | February 2026 | Hat Care Guide | https://helenkaminski.com.au/pages/hat-care | 300 | Existing Copy: Optimisation & FAQs | hat care tips |  |  | 2 | 0.5 | 1 | 0.5 | 0.5
Month 2 | February 2026 | Raffia Hats | https://helenkaminski.com.au/collections/raffia-hats | 300 | Existing Copy: Optimisation | raffia hats |  |  | 2 | 0.5 | 1 | 0.5 | 0.5
Month 2 | February 2026 | Sun Hats US | https://helenkaminski.com/collections/sun-hats | 150 | Existing Copy: Optimisation | sun hats | localisation |  | 1 | 0.5 | 0.5 | 0.5 | 0
Month 2 | February 2026 | Hat Care US | https://helenkaminski.com/pages/hat-care | 150 | Existing Copy: Optimisation & FAQs | hat care | localisation |  | 1 | 0.5 | 0.5 | 0.5 | 0
Month 3 | March 2026 | Winter Hats | https://helenkaminski.com.au/collections/winter-hats | 300 | Existing Copy: Optimisation | winter hats australia |  |  | 2 | 0.5 | 1 | 0.5 | 0.5
Month 3 | March 2026 | Knit Beanies | https://helenkaminski.com.au/collections/beanies | 300 | New Page: Optimisation | knit beanies australia |  |  | 2 | 0.5 | 1 | 0.5 | 0.5

## 5. Links
Task | Description | Hours | Cadence
Digital PR Outreach | Pitch to AU lifestyle publications | 0 | Monthly
Guest Post Sourcing | Identify and pitch guest post opportunities | 0 | Monthly
Link Reclamation | Recover unlinked brand mentions | 0 | Quarterly

## Roadmap
SEO Roadmap 2026
Month 1 | Technical audit, redirect fixes, schema setup | Month 1 | 2026-01-31 | https://helenkaminski.com.au/ https://helenkaminski.com.au/collections/womens-hats
Month 2 | CWV remediation, internal linking pass | Month 2 | 2026-02-28 | https://helenkaminski.com.au/collections/sun-hats
Month 3 | Schema expansion, crawl error resolution | Month 3 | 2026-03-31 | https://helenkaminski.com.au/collections/winter-hats
Month 4 | Page speed optimisation | Month 4 | 2026-04-30 | https://helenkaminski.com.au/collections/autumn-hats
Month 5 | Structured data audit | Month 5 | 2026-05-31 | https://helenkaminski.com.au/collections/travel-hats
Month 6 | Mid-year technical review | Month 6 | 2026-06-30 | https://helenkaminski.com.au/collections/resort-hats